## SCRA retention - 310824
Scottish Children's Reporter Administration (SCRA) Retention Policy Statement - 31/8/24
1 | Policy on retention in construction contracts is as set out below with respect to Chapter 17 in Handbook 1
of The Client Guide to Construction Projects
| 1.1 | Derived directly and solely from it |  | No
SCRA's policy on retention in construction projects is that we do align to the above Client Guide on Construction Projects, however, as per Q1.2 response below, there are occasions where we take into consideration our Consultants opinion.
| 1.2 | Derived from it and other sources | Yes
SCRA additionally take advice from professional Consultants who we have engaged to assist us, and will consider alongside their advice what, if any, retention should be applied.
| 1.3 | Diverges from it |  | No
SCRA does not diverge from it.
| 1.4 | Not required to and does not follow it |  | No
SCRA is required and does follow it.
| 1.5 | Other |  | No
None
2 | The strategic approach to retention taken by Scottish Children's Reporter Administration is as set out below
| 2.1 | Aims for the contractor to deliver zero defects | Yes
Our overall strategic approach is for our contractors to deliver zero defects through our effective planning, procuring and contract management of projects.
| 2.2 | Retention is applied in all construction contracts regardless of project-specific factors |  | No
Our approach is that where retention can be minimalised or not be applied at all, we do so.
| 2.3 | Retention is applied uniformly in all construction contracts regardless of project-specific factors |  | No
Our approach is that we do not uniformly apply retention, but it is considered on a case by case basis.
| 2.4 | Some construction contracts apply retention | Yes
SCRA currently use a suite of standard contracts, however our approach is that we do apply retention in some construction contracts by taking into account various factors such as contract value, duration of works, project complexity, risks, financial due diligence and at the advice of our professional Consultant (if applicable) where it is fair and proportionate to do so, but we do not have specific thresholds to adhere to and generally retention is around 5%, thereafter reducing to 2.5% at practical completion stage on a varied 3-12 month defect liability period.
| 2.5 | Some construction contracts do not apply retention | Yes
Our approach is that we do not apply retention in some construction contracts by taking into account various factors such as contract value, duration of works, risks, financial due diligence and at the advice of our professional Consultant (if applicable) where it is fair and proportionate to do so, but we do not have specific thresholds to adhere to.
| 2.6 | Other |  | No
None
3 | Policy on retention in construction contracts takes account of the following factors
| 3.1 | Project type | Yes
Our Work projects mainly consist of small building works and interior refurbishment to existing assets.
| 3.2 | Project value | Yes
Our Construction projects vary in size and complexity between £10K - £1M. SCRA's annual Property Capital budget allocation, averages at around £1.5M.
| 3.3 | Project duration | Yes
Projects can generally range from several week to 6 months.
| 3.4 | Project design complexity and/or novelty including ergonomics and buildability. | Yes
Our projects mainly consist of straightforward refurbishments or small building works.
| 3.5 | Extent of off-site and on-site work specified or implied by the design |  | No
SCRA only undertake on-site work.
| 3.6 | Availability of project materials and associated trade skillsets for the |  | No
required standard of finish
SCRA projects are generally straightforward refurbishment type contracts or small building works. Standard finishes & skillsets are dealt with via procurement documents.
| 3.7 | Project procurement route, see Handbook 2 Chapter 5 of | Yes
The Client Guide to Construction Projects
SCRA’s project procurement route uses a traditional SBCC Minor Works building contract 2016 in the majority of instances, however in specific circumstances, we would review our position and consider other options depending on the type/value/risk of the contract required, as described in the Construction Procurement Handbook 2, Chapter 5, and taking any additional advice from any professional Consultant we engaged.
| 3.8 | Project procurement procedure, see Chapter 2 Section 3 of | Yes
The Public Contracts (Scotland) Regulations 2015
SCRA’s project procurement procedure is conducted via an Open Procedure/Contract notice or Quick Quote via Public Contracts Scotland (PCS) portal where all tender documents are transparent, open, visible and registered, which also allows contractor questions and clarifications to be asked and answered in an open and fair manner.
| 3.9 | Form of contract | Yes
The type of work we are involved in uses SBCC contract, and in specific circumstances we would consider other options depending on type of contract/value/complexity/risks and we would review the position at that time.
| 3.1 | Volume, detail and format of as-built, operating and maintenance |  | No
information, including compliance with BIM requirements
Not applicable
| 3.11 | Market conditions |  | No
Not applicable
| 3.12 | Availability and affordability of a trust-based commercial bank account |  | No
into which the main contractor can deposit subcontractors’ retention
SCRA does not use this type of bank account.
| 3.13 | Inspection and testing regime for materials and workmanship on site |  | No
SCRA employs Consultants to monitor the standards of workmanship, and carry out inspections, on site.
| 3.14 | Targeting distinct activities/trades/elements for specific retention treatment |  | No
SCRA does not use this type of targeting treatment.
| 3.15 | Implementing a payment process triggered by demonstrable |  | No
milestone events on site instead of set intervals of time
SCRA employs Consultants, and the staged payment intervals are agreed at the pre-start meeting (which minimally includes SCRA, the Consultant and the Contractor, and depending on the complexity of the project can involve sub-contractors as well), depending on the nature of the contract.
| 3.16 | Holding no retention on temporary works procured directly by the public |  | No
contract that will not be permanently incorporated into the completed works
SCRA do not undertake temporary works contracts.
| 3.17 | Enabling the replication of main contract retention provisions in successive |  | No
contracts along the supply chain as far as reasonably possible
SCRA's contracts have provisions in our Procurement documents which state that all contractors should offer the same payment terms to all sub-contractors.
| 3.18 | Other factor(s) |  | No
None